AIRA

AI-Native Enterprise Platform

Sprint-0 and Foundation Build Execution Plan

Repository Bootstrap | Foundation Build | Ready-to-Code Execution | AVCI Evidence

Mandatory Execution Position Sprint-0 is not a coding sprint for business features. It is the controlled foundation build that proves the AIRA repository, environment, pipeline, security, MicroFunction skeleton, evidence model, and AI-assisted engineering controls are ready before business module development starts.

Version 1.0 | April 2026 | INTERNAL CONFIDENTIAL

# Document Control

| Property | Value |
| --- | --- |
| Document ID | AIRA-DOC-019 |
| Document Title | AIRA Sprint-0 and Foundation Build Execution Plan |
| Version | v1.0 - Initial Execution Baseline |
| Classification | INTERNAL CONFIDENTIAL |
| Status | FOR ARCHITECTURE REVIEW BOARD / ENGINEERING ADOPTION |
| Owner | Solutions Architecture Office / IT Head |
| Co-Owners | Software Development Lead, DevSecOps Lead, Security Administrator, System Administrator, DBA, QA Lead |
| Effective Date | Upon approval and repository bootstrap kickoff |
| Review Cadence | At Sprint-0 closeout; then quarterly or on material scope, stack, security, or delivery-plan change |
| Primary Audience | Solutions Architect, Software Developers, DevSecOps, System Administrator, Security Administrator, DBA, QA/SDET, AI Engineers, Internal Audit |
| Companion Documents | 01A Enterprise Design Principles and SOLID Enforcement Layer; 01 AVCI v3.0; 02 Engineering Blueprint v5.0; 03 Developer Guide v4.0; 04 Technology Stack v8.0; 06 CLAUDE.md Reference v3.0; 08 Unit Testing v3.0; 10 MicroFunction v3.0; 11 DevSecOps v3.0; 18 Repository Bootstrap Guide v1.0 |
| Purpose | Define the Sprint-0 execution plan that converts AIRA standards into a working foundation repository, environment, CI/CD evidence path, security baseline, MicroFunction skeleton, and ready-to-code delivery capability. |

# Version 1.0 Release Notes

| Area | Baseline Decision |
| --- | --- |
| Sprint purpose | Establish controlled foundation readiness before business-feature development. |
| Delivery model | Time-boxed execution using workstreams, epics, user stories, acceptance gates, and evidence packs. |
| Governance alignment | Applies AVCI v3.0, 01A Enterprise Design Principles, SOLID, Clean Architecture, DDD, SBAC, policy-as-code, TDD, and architecture fitness functions. |
| Development boundary | Business module coding is deferred until Ready-to-Code and Ready-to-Develop gates are passed. |
| Output expectation | At Sprint-0 closeout, the team has a working skeleton, pipelines, repository controls, local/dev environment, initial MicroFunction sample, and evidence model. |

# Table of Contents

1. Executive Summary

2. Purpose, Scope, and Authority

3. Sprint-0 Operating Principles

4. Sprint-0 Outcomes and Exit Criteria

5. Sprint-0 Workstream Model

6. Sprint-0 Backlog and User Stories

7. Execution Timeline and Milestones

8. Team Roles, RACI, and Operating Cadence

9. Governance Gates and Evidence Pack

10. Technical Foundation Build Details

11. Risks, Dependencies, Assumptions, and Decisions

12. Sprint-0 Closeout and Handoff to Sprint 1

Appendix A. Sprint Board Template

Appendix B. User Story Template

Appendix C. Evidence Record Template

Appendix D. AVCI Compliance Summary

# 1. Executive Summary

AIRA Sprint-0 is the controlled execution bridge between the approved architecture standards and the first production-bound development work. It is designed to establish a clean, governed, reproducible, and evidence-producing foundation before the team begins business-feature development.

The sprint focuses on foundation readiness: repository bootstrap, Golden Source controls, devcontainer and workstation standards, CI/CD gates, architecture fitness checks, security baseline, MicroFunction runtime skeleton, sample transaction, API and database contract patterns, observability hooks, and AI-assisted development controls.

Executive Decision Controlled foundation development may start under Sprint-0 once the Ready-to-Start Gate is approved. Business module coding must wait until the Ready-to-Code Gate and relevant module readiness criteria are satisfied.

## 1.1 Strategic Outcomes

| Outcome | Sprint-0 Delivery Mechanism |
| --- | --- |
| Controlled start | The team starts with approved repositories, branch protection, CODEOWNERS, templates, and CI gates. |
| Developer readiness | Every developer has a clean environment, approved toolchain, devcontainer, AI usage acknowledgement, and local validation path. |
| Architecture enforcement | SOLID, Clean Architecture, DDD, ports-and-adapters, dependency direction, and no-bypass rules are checked by code review and automated fitness functions. |
| Security from day one | Keycloak/AD, Vault/secrets pattern, SBAC/OPA hooks, no-secrets scanning, and classification-aware data handling are established early. |
| Testing discipline | TDD, deterministic unit tests, contract tests, ArchUnit checks, and evidence artifacts are required from the first mergeable code. |
| MicroFunction proof | A sample configurable transaction demonstrates runtime assembly, idempotency, audit, error handling, compensation, outbox, and safe response. |
| AI governance | ChatGPT/Codex/Claude usage follows CLAUDE.md hierarchy, Harness boundary, LiteLLM-only model routing for application flows, and human accountability. |
| Evidence readiness | Each sprint output carries AVCI evidence: owner, source, validation, classification, approval, and improvement path. |

## 1.2 What Sprint-0 Is Not

It is not a business-feature sprint. Business-specific modules should not proceed until contracts, acceptance criteria, classifications, and test cases are ready.

It is not a shortcut around architecture. Sprint-0 must prove the architecture controls before allowing higher delivery velocity.

It is not an autonomy license for AI tools. AI may draft and assist, but humans remain accountable and all controlled actions follow policy gates.

It is not a one-time setup task. Sprint-0 establishes repeatable patterns that must remain enforced throughout the project lifecycle.

# 2. Purpose, Scope, and Authority

## 2.1 Purpose

This plan defines the work, sequencing, acceptance criteria, roles, and evidence required to complete Sprint-0 for AIRA. It provides the actionable execution model that the Software Development, DevSecOps, Security, Infrastructure, DBA, QA, and AI Engineering teams can follow before regular feature delivery begins.

## 2.2 In Scope

Repository bootstrap, branch protection, CODEOWNERS, PR/MR templates, issue templates, labels, and baseline governance files.

Golden Source baseline for approved dependencies, container images, plugins, templates, prompts, guardrails, and pipeline artifacts.

Developer workstation and devcontainer readiness aligned with the Greenfield Environment Standard.

Initial CI/CD pipeline with test, scan, policy, architecture, and evidence gates.

Base service skeletons for gateway, workflow, retrieval, orchestrator, harness, admin-governance, and sample bounded-context service.

MicroFunction runtime skeleton and one sample transaction demonstrating standard controls and one isolated business function.

Initial contract registry, database migration baseline, observability baseline, security baseline, and AI governance baseline.

Sprint-0 evidence pack and closeout report.

## 2.3 Out of Scope

Full business module delivery, except a controlled sample transaction used to prove the framework.

Production deployment, customer data migration, external system go-live, or production AI model use.

Full DR/BCP, UAT, and production operations manuals, except starter runbook stubs needed for foundation readiness.

Unapproved direct integration to model providers, production databases, external customer systems, or unmanaged public repositories.

## 2.4 Authority and Conflict Resolution

| Authority Level | Document / Control | Sprint-0 Impact |
| --- | --- | --- |
| L0 | Architecture Board / Consolidated Architecture Decisions | Controls major architecture direction and unresolved conflicts. |
| L1 | 02-AIRA Engineering Blueprint v5.0 | Controls service boundaries, target flows, data design, workflows, AI orchestration, and evidence model. |
| L1 | 11-AIRA AI-Native DevSecOps Standard v3.0 | Controls lifecycle, CI/CD gates, promotion, AI-assisted work, and evidence discipline. |
| L2 | 01-AIRA AVCI v3.0 and 01A Enterprise Design Principles | Controls universal quality, SOLID, architecture boundaries, testability, security, observability, reversibility, and evidence. |
| L2 | Specialist Standards | Developer Guide, Unit Testing, Security, API, Database, CLAUDE.md, Greenfield, Skills, MicroFunction, and Knowledge Governance standards define domain-specific rules. |
| L3 | This Sprint-0 Plan | Controls execution sequence and acceptance criteria for the foundation build. |

# 3. Sprint-0 Operating Principles

Sprint-0 must demonstrate that the AIRA delivery engine is governed before it becomes fast. The following rules are non-negotiable for all foundation work.

| ID | Principle | Sprint-0 Meaning |
| --- | --- | --- |
| S0-1 | AVCI by construction | Every Sprint-0 artifact must have owner, source, version, classification, verification evidence, and improvement path. |
| S0-2 | Architecture first | Repositories, services, packages, and pipelines must follow the approved architecture before business code is added. |
| S0-3 | SOLID and boundary enforcement | Base code must prove single responsibility, dependency direction, clean package boundaries, ports/adapters separation, and no infrastructure leakage into domain logic. |
| S0-4 | Configuration-first | Runtime behavior should be expressed through approved configuration, templates, policies, and MicroFunction catalog entries wherever feasible. |
| S0-5 | Secure by default | No secret, credential, PII, direct provider key, or unrestricted administrative path may enter the repository or logs. |
| S0-6 | TDD and deterministic evidence | Mergeable code must include deterministic unit tests, contract tests where relevant, and CI evidence. |
| S0-7 | Fail-safe, not fail-open | If identity, policy, guardrails, secrets, or audit dependencies are unavailable, controlled operations are blocked. |
| S0-8 | One contribution path | All changes enter through protected Git workflow, review, CI gates, signed artifacts, and evidence retention. |
| S0-9 | AI assistance is bounded | AI drafts and analyzes; humans approve. Tool execution follows CLAUDE.md, Harness, SBAC, OPA, and audit boundaries. |
| S0-10 | Rebuildability and reversibility | Every foundation component must be reproducible from source and reversible through rollback, forward-fix, or rebuild procedure. |

# 4. Sprint-0 Outcomes and Exit Criteria

## 4.1 Required Deliverables

| ID | Deliverable | Acceptance Description |
| --- | --- | --- |
| D1 | Repository baseline | Root repository or controlled multi-repo baseline with README, CLAUDE.md, CODEOWNERS, templates, branch protection, and lock files. |
| D2 | Golden Source baseline | Approved source paths for dependencies, container images, devcontainer base, templates, prompts, guardrails, and pipeline actions. |
| D3 | Development environment baseline | Devcontainer and workstation setup instructions verified by at least two developers. |
| D4 | CI/CD evidence pipeline | Build, lint, unit test, architecture test, dependency scan, secret scan, SAST, SBOM, and evidence pack generation. |
| D5 | Service skeletons | Compile-ready Spring/React/service skeletons aligned with architecture package rules. |
| D6 | Security baseline | Keycloak/AD integration stub or local dev profile, Vault/secrets pattern, OPA policy scaffold, SBAC placeholders, and audit envelope. |
| D7 | MicroFunction proof | Sample transaction proving runtime assembly, standard steps, idempotency, error handling, audit, outbox, and safe response. |
| D8 | Contract and migration baseline | OpenAPI/AsyncAPI skeletons, Flyway baseline, schema ownership pattern, and test fixtures. |
| D9 | Observability baseline | Trace/log/metric correlation using OpenTelemetry conventions and local/development observability target. |
| D10 | AI governance baseline | CLAUDE.md rules, AI usage declaration, prompt/guardrail/model registry folders, and no direct provider SDK enforcement. |
| D11 | Evidence pack | Sprint-0 closeout evidence with AVCI summary, test reports, scan results, decisions, risks, and open actions. |

## 4.2 Sprint-0 Exit Criteria

| Gate | Mandatory Criteria | Evidence Required |
| --- | --- | --- |
| Ready-to-Code | Developers can clone, build, run tests, open a devcontainer, and submit a sample PR through protected workflow. | Clone/build log, devcontainer verification, PR evidence, reviewer approval. |
| Architecture Gate | Service/package boundaries pass architecture fitness checks and manual architecture review. | ArchUnit or equivalent report, package dependency graph, architecture review note. |
| Security Gate | Secret scan, SAST baseline, policy checks, no direct provider SDKs, no unmanaged credentials, and safe local profile pass. | Scan reports, OPA/Conftest output, secret scan output, waiver register if any. |
| Testing Gate | TDD baseline, deterministic unit tests, sample contract tests, changed-line coverage threshold, and mutation-test plan exist. | CI test reports, coverage report, test evidence schema. |
| MicroFunction Gate | Sample transaction executes through standard envelope with audit, idempotency, error path, and safe response. | Demo evidence, logs/traces, audit record sample, test output. |
| Evidence Gate | Every material Sprint-0 artifact has AVCI evidence and owner. | Evidence register, PR/MR summaries, traceable links. |

# 5. Sprint-0 Workstream Model

Sprint-0 is executed through parallel workstreams with daily integration. Each workstream produces independently reviewable artifacts but must converge into one foundation demo and closeout evidence pack.

| ID | Workstream | Owner | Primary Outputs | Key Dependency |
| --- | --- | --- | --- | --- |
| WS1 | Governance and Backlog | Solutions Architect / IT Head | Sprint board, issue taxonomy, acceptance gates, evidence register, decision log | All workstreams |
| WS2 | Repository and Golden Source | DevSecOps Lead | Repo baseline, branch protection, CODEOWNERS, templates, golden-source paths | 18 Repository Bootstrap Guide |
| WS3 | Developer Environment | System Administrator + Dev Lead | Devcontainer, local compose/dev profile, workstation validation, onboarding evidence | Greenfield Environment |
| WS4 | CI/CD and Evidence | DevSecOps + QA Lead | Pipeline skeleton, test/scan/SBOM/signing/evidence stages | Repository baseline |
| WS5 | Security and Access | Security Administrator | Keycloak/AD pattern, Vault pattern, OPA/SBAC scaffold, audit controls | Security Standard |
| WS6 | Service Skeletons | Software Development Lead | Gateway, workflow, retrieval, orchestrator, harness, admin, sample domain skeletons | Developer Guide, Blueprint |
| WS7 | MicroFunction Runtime | Backend Lead | Runtime assembly skeleton, sample transaction, standard envelope, error path | MicroFunction docs |
| WS8 | API and Event Contracts | Integration Lead / Senior Dev | OpenAPI/AsyncAPI registry, sample contracts, error/idempotency headers | API Contract Standard |
| WS9 | Database and Migration | DBA + Backend Lead | Flyway baseline, schema ownership, audit columns, outbox/idempotency tables | Database Standard |
| WS10 | Observability | SRE / DevSecOps | OTel correlation, structured logging, metric names, trace/log linkage | Technology Stack |
| WS11 | AI Governance | AI Engineering Lead | Prompt/guardrail/model-alias folders, no direct model calls, AI evidence template | CLAUDE.md, Skills Framework |
| WS12 | Knowledge and Documentation | Knowledge Steward | Obsidian/LLM Wiki folder stubs, source index, closeout pack | Knowledge Governance |

# 6. Sprint-0 Backlog and User Stories

The backlog below is the initial execution baseline. Teams may split stories into smaller tasks, but acceptance criteria must not be weakened without Architecture and DevSecOps approval.

| Epic | Theme | Story ID | User Story | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| E01 | Repository Bootstrap | S0-US-001 | As a developer, I can clone the approved AIRA repository and see the required governance files. | README, CLAUDE.md, CODEOWNERS, PR template, issue templates, branch protection evidence. |
| E01 | Repository Bootstrap | S0-US-002 | As a reviewer, I can enforce code ownership and protected branch review before merge. | CODEOWNERS triggers required reviewers; direct pushes to main are blocked. |
| E02 | Golden Source | S0-US-003 | As DevSecOps, I can source approved base images, dependencies, and templates from controlled locations. | Golden Source register and signed/approved artifact paths exist. |
| E03 | Developer Environment | S0-US-004 | As a developer, I can open the devcontainer and run the baseline build without manual tool installation. | Devcontainer opens, build passes, tests run, documented setup time captured. |
| E04 | CI/CD Evidence | S0-US-005 | As QA/DevSecOps, I can run CI with unit tests, architecture checks, scans, SBOM, and evidence export. | Pipeline reports are retained and linked to PR. |
| E05 | Security Baseline | S0-US-006 | As Security Admin, I can verify no secrets, raw PII, or provider credentials are present in repository, logs, or tests. | Secret scan pass; synthetic fixtures only; no real tokens. |
| E05 | Security Baseline | S0-US-007 | As a developer, I can call a protected sample endpoint using local/dev identity profile. | JWT/dev identity stub, policy decision, audit record, safe denial path. |
| E06 | Service Skeletons | S0-US-008 | As a developer, I can build and run the base Spring service skeleton with clean package boundaries. | Compile pass, package rules pass, health endpoint, trace ID propagation. |
| E07 | MicroFunction Runtime | S0-US-009 | As a solution architect, I can configure and run one sample transaction through standard MicroFunction steps. | Runtime config, standard step list, business step isolation, success path. |
| E07 | MicroFunction Runtime | S0-US-010 | As QA, I can verify the sample transaction error path, retry policy, compensation, audit, and safe response. | Unit/component tests, error classification, audit/event evidence, DLQ stub where applicable. |
| E08 | API/Event Contracts | S0-US-011 | As an integration developer, I can publish a sample OpenAPI and AsyncAPI contract before implementation. | Contracts linted, versioned, and referenced by service skeleton. |
| E09 | Database/Migration | S0-US-012 | As DBA, I can apply Flyway baseline migrations for framework tables in a clean database. | Flyway output, rollback/forward-fix note, schema owner, RLS placeholder. |
| E10 | Observability | S0-US-013 | As SRE, I can correlate a sample request across log, trace, metric, and audit evidence. | Trace_id/request_id present in service log and audit event. |
| E11 | AI Governance | S0-US-014 | As a developer using AI assistance, I can declare AI involvement in PR evidence and follow CLAUDE.md rules. | PR summary includes model/tool, intent, files affected, tests run, human checker. |
| E12 | Knowledge | S0-US-015 | As a knowledge steward, I can index approved Sprint-0 outputs into the Obsidian/LLM Wiki structure without drafts becoming authoritative. | Folder structure, metadata, status tags, source links, approval state. |

# 7. Execution Timeline and Milestones

The timeline uses relative Sprint-0 days to avoid dependency on calendar changes. The recommended duration is two to four weeks depending on team availability, environment procurement, and infrastructure readiness. T0 is the approved Sprint-0 kickoff date.

| Phase | Target Window | Primary Activities | Milestone / Gate |
| --- | --- | --- | --- |
| S0.0 Kickoff and Control Setup | T0 to T0+1 | Confirm scope, owners, workstreams, sprint board, evidence register, risk register, and communication cadence. | Ready-to-Start Gate approved. |
| S0.1 Repository and Environment Baseline | T0+1 to T0+5 | Create repository, branch protection, CODEOWNERS, devcontainer, local setup, dependency baseline, Golden Source paths. | Clone/build/devcontainer demo. |
| S0.2 CI/CD and Security Baseline | T0+4 to T0+9 | Implement initial pipeline stages, secret scan, SAST, unit test, architecture checks, SBOM, OPA/Conftest scaffold. | First passing guarded PR. |
| S0.3 Service Skeleton and Contracts | T0+7 to T0+13 | Create service skeletons, OpenAPI/AsyncAPI contracts, Flyway baseline, error model, trace/log/audit conventions. | Service skeleton integration demo. |
| S0.4 MicroFunction Proof | T0+10 to T0+17 | Implement runtime assembly skeleton, sample transaction, standard steps, STP-BUS sample, error/retry/compensation path. | MicroFunction sample demo. |
| S0.5 Evidence, Closeout, and Handoff | T0+15 to T0+20 | Complete evidence pack, close risks/decisions, update docs, prepare Sprint 1 backlog, conduct formal defense/demo. | Ready-to-Code Gate decision. |

## 7.1 Milestone Flow

Sprint-0 Milestone Flow Kickoff -> Repository baseline -> Developer environment -> CI/CD security gates -> Service skeletons -> Contract and migration baseline -> MicroFunction proof -> Evidence pack -> Ready-to-Code approval.

# 8. Team Roles, RACI, and Operating Cadence

## 8.1 Core Roles

| Role | Sprint-0 Responsibility |
| --- | --- |
| Solutions Architect / IT Head | Owns architecture decisions, Sprint-0 acceptance gates, conflict resolution, and final Ready-to-Code decision. |
| Software Development Lead | Owns service skeletons, developer task breakdown, code quality, package boundaries, and sample transaction implementation. |
| DevSecOps Lead | Owns repository bootstrap, CI/CD pipeline, Golden Source integration, evidence pack automation, and branch protection. |
| Security Administrator | Owns identity, secrets, SBAC/OPA, secret scanning, security baseline, AI execution boundary, and security waivers. |
| System Administrator | Owns developer workstation baseline, server provisioning, local/dev runtime dependencies, and environment readiness. |
| Database Administrator | Owns Flyway baseline, schema ownership, database policy, RLS placeholders, backup/restore readiness, and migration evidence. |
| QA / SDET Lead | Owns TDD discipline, test strategy, deterministic tests, contract tests, coverage gates, and validation evidence. |
| AI Engineering Lead | Owns prompt/guardrail/model-alias registry baseline, AI evidence, and no-direct-model-call checks. |
| Knowledge Steward | Owns Obsidian/LLM Wiki folder structure, metadata, source indexing, and closeout knowledge promotion. |

## 8.2 RACI Matrix

| Activity | SA/IT Head | Dev Lead | DevSecOps | Security | SysAdmin | DBA | QA | AI Lead |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint-0 scope and gate approval | A | C | C | C | C | C | C | C |
| Repository bootstrap | C | C | A/R | C | I | I | C | C |
| Branch protection and CODEOWNERS | A | R | R | C | I | I | C | C |
| Devcontainer and workstation validation | C | R | C | C | A/R | I | C | I |
| CI/CD pipeline and evidence pack | C | C | A/R | C | I | I | R | C |
| Security baseline and OPA/SBAC | A | C | R | A/R | C | C | C | C |
| Service skeletons | C | A/R | C | C | I | C | C | C |
| Database migrations | C | R | C | C | I | A/R | C | I |
| MicroFunction sample transaction | A | A/R | C | C | I | C | R | C |
| AI governance baseline | A | C | C | C | I | I | C | A/R |
| Closeout evidence and handoff | A | R | R | R | C | C | R | R |

## 8.3 Operating Cadence

| Ceremony | Frequency | Purpose | Required Output |
| --- | --- | --- | --- |
| Daily foundation stand-up | Daily during Sprint-0 | Surface blockers, integration risks, gate status, and evidence gaps. | Updated board, blockers, owner actions. |
| Architecture checkpoint | Twice weekly | Validate boundaries, design decisions, and implementation alignment. | Decision notes, ADR/TDL updates, unresolved conflicts. |
| Security and pipeline checkpoint | Twice weekly | Review scan failures, policy gates, secrets handling, and environment controls. | Security findings, waiver log if any, remediation tasks. |
| Sprint-0 demo | At each milestone | Show working evidence, not slide-only status. | Demo recording or screenshots, test reports, reviewer notes. |
| Closeout defense | End of Sprint-0 | Formal confirmation that foundation is ready for controlled Sprint 1 development. | Ready-to-Code decision and evidence pack. |

# 9. Governance Gates and Evidence Pack

Sprint-0 evidence must be treated as part of the deliverable. A working repository without evidence is not ready for AIRA development.

| Gate ID | Gate Name | Pass Criteria | Evidence Artifacts |
| --- | --- | --- | --- |
| G0 | Ready-to-Start | Scope, owners, repository target, environment approach, and Sprint-0 board are approved. | Approved sprint plan, RACI, risk log, board link/export. |
| G1 | Repository Control | Protected branch, CODEOWNERS, templates, CLAUDE.md, and contribution rules are active. | Repository settings export, sample blocked direct push, reviewer trigger evidence. |
| G2 | Environment Control | At least two developers can rebuild environment from documented instructions. | Setup logs, screenshots, devcontainer build output, issue log. |
| G3 | Pipeline Control | CI runs deterministic test, scan, policy, architecture, and evidence stages. | Pipeline output, scan reports, SBOM, coverage, architecture report. |
| G4 | Security Control | No secrets/PII/provider keys; identity, OPA/SBAC, Vault pattern, and audit scaffold exist. | Secret scan pass, policy test output, sample audit record, security review. |
| G5 | Foundation Code Control | Base services compile, package boundaries pass, contracts exist, migrations apply. | Build logs, OpenAPI/AsyncAPI lint, Flyway log, ArchUnit result. |
| G6 | MicroFunction Proof | Sample transaction proves success path, failure path, idempotency, audit, event/outbox, and safe response. | Demo, unit/component tests, logs/traces, sample audit records. |
| G7 | Ready-to-Code | All critical gates pass or have approved time-bound waivers; Sprint 1 backlog is ready. | Closeout pack, waiver register, readiness decision, Sprint 1 backlog. |

## 9.1 Sprint-0 Evidence Pack Structure

| Folder | Contents |
| --- | --- |
| /evidence/sprint-0/00-control | Approved plan, RACI, sprint board export, risk log, decision log. |
| /evidence/sprint-0/01-repository | Repo settings, branch protection, CODEOWNERS, templates, CLAUDE.md lock. |
| /evidence/sprint-0/02-environment | Devcontainer output, setup logs, workstation validation, drift check. |
| /evidence/sprint-0/03-pipeline | CI logs, test reports, coverage, architecture fitness, scans, SBOM, provenance. |
| /evidence/sprint-0/04-security | Secret scan, OPA tests, SBAC baseline, Vault pattern, audit samples. |
| /evidence/sprint-0/05-code | Service skeleton review, package boundary report, contracts, migrations. |
| /evidence/sprint-0/06-microfunction | Sample transaction configuration, tests, logs, traces, audit, error path evidence. |
| /evidence/sprint-0/07-closeout | Closeout report, demo evidence, open actions, waiver register, Sprint 1 handoff. |

# 10. Technical Foundation Build Details

## 10.1 Minimum Repository Layout for Sprint-0

aira-platform/
|-- README.md
|-- CLAUDE.md
|-- .claude-md.lock
|-- CODEOWNERS
|-- docs/
|   |-- adr/
|   |-- standards/
|   `-- sprint-0/
|-- services/
|   |-- gateway-service/
|   |-- workflow-service/
|   |-- retrieval-service/
|   |-- orchestrator-service/
|   |-- harness-service/
|   |-- admin-governance-service/
|   `-- sample-domain-service/
|-- libs/
|   |-- aira-common/
|   |-- aira-security/
|   |-- aira-observability/
|   `-- aira-microfunction-core/
|-- contracts/
|   |-- openapi/
|   |-- asyncapi/
|   `-- schemas/
|-- db/
|   `-- migration/
|-- ai/
|   |-- prompts/
|   |-- guardrails/
|   |-- models/
|   `-- evaluations/
|-- infra/
|   |-- devcontainer/
|   |-- compose/
|   |-- kubernetes/
|   `-- policy/
|-- tests/
|   |-- contract/
|   |-- architecture/
|   `-- fixtures/
`-- evidence/
    `-- sprint-0/

## 10.2 Minimum CI/CD Stages

| Stage | Required Checks | Reject Condition |
| --- | --- | --- |
| Prepare | Checkout, dependency cache from approved source, version lock validation. | Unpinned dependency or direct public source bypass. |
| Static quality | Formatting, linting, forbidden imports, package boundary checks. | Direct provider SDK, controller business logic, infrastructure leakage, bypass flags. |
| Unit tests | Deterministic unit tests, changed-line coverage, test fixtures synthetic only. | Flaky tests, real PII, real network, uncontrolled clock/randomness. |
| Architecture tests | SOLID, Clean Architecture, DDD boundary, ports/adapters, dependency direction. | Cross-context write, domain depends on infrastructure, unapproved package cycle. |
| Security scans | Secret scan, SAST, dependency/SCA, container scan where applicable. | Critical/high unapproved finding, secret or token exposure. |
| Policy checks | OPA/Conftest, Kubernetes/IaC policy, CLAUDE.md rule enforcement. | Policy deny without approved waiver. |
| Contracts and migrations | OpenAPI/AsyncAPI lint, compatibility checks, Flyway validate/migrate clean DB. | Breaking contract, migration checksum failure, unmanaged DDL. |
| SBOM and evidence | Generate SBOM, test reports, scan reports, AVCI evidence pack. | Missing evidence, incomplete owner/classification/verification data. |

## 10.3 Sample Transaction Scope

Sprint-0 should use one low-risk sample transaction to prove the framework. The transaction must be synthetic and must not use production customer data. A recommended example is SAMPLE-CASE-CREATE or SAMPLE-DOCUMENT-INTAKE-STUB.

| Step | Required Proof |
| --- | --- |
| Receive and correlate | Request receives trace_id, request_id, tenant placeholder, and correlation context. |
| Session and security | Actor context is resolved and authorization/policy is evaluated. |
| Parse, normalize, validate | Payload is transformed into typed request and invalid input is safely rejected. |
| Idempotency and concurrency | Duplicate request does not double-create business effect. |
| Business function | Only the STP-BUS-* sample function contains domain-specific behavior. |
| Persistence and outbox | State and event intent are committed safely through approved pattern. |
| Audit and observability | Audit record, log, trace, and metric share correlation IDs. |
| Error path | Failure is classified, retried or not retried by policy, compensated if required, and returned as safe error response. |

# 11. Risks, Dependencies, Assumptions, and Decisions

| Risk ID | Risk | Impact | Mitigation / Control |
| --- | --- | --- | --- |
| R1 | Team starts business coding before foundation gates pass. | Architecture drift, inconsistent patterns, rework. | Block business-feature stories until Ready-to-Code Gate is approved. |
| R2 | Repository controls are configured manually and not reproducibly documented. | Audit weakness and inconsistent future repositories. | Export settings, document branch protection, and store templates in Golden Source. |
| R3 | Developers bypass devcontainer or install unapproved tools locally. | Drift, supply-chain exposure, non-reproducible builds. | Greenfield controls, workstation validation, pre-commit and CI enforcement. |
| R4 | CI becomes too heavy and slows early iteration. | Team bypasses quality checks. | Use staged gates: fast local checks, required PR checks, heavier scheduled scans. |
| R5 | AI-generated code weakens architecture boundaries. | Maintainability and security risk. | CLAUDE.md rules, architecture tests, reviewer checklist, AI involvement declaration. |
| R6 | Security baseline is deferred. | Secrets, identity, and policy issues discovered late. | Require secret scan, OPA/SBAC scaffold, Vault pattern, and safe local profile in Sprint-0. |
| R7 | MicroFunction framework becomes over-engineered before proof. | Delay and complexity. | Build only the minimum vertical slice, then evolve through tests and ADRs. |

## 11.1 Sprint-0 Assumptions

AIRA standards vNext documents are the current working baseline for Sprint-0 implementation.

A repository platform is available or approved for use before T0.

At least one DevSecOps engineer, one backend developer, one QA/SDET, one security representative, one DBA, and one system administrator are available for Sprint-0 execution.

All test data, fixtures, prompts, and examples are synthetic and classification-safe.

Production data, production credentials, and production systems are not used during Sprint-0.

## 11.2 Decision Log Requirements

Any material deviation from this plan requires an ADR, TDL, or waiver depending on impact. Sprint-0 must not hide design decisions inside chat messages, temporary notes, or source comments.

| Decision Type | Trigger | Required Artifact |
| --- | --- | --- |
| ADR | Material architecture, security, data, workflow, AI, or platform decision. | ADR with 20-principle impact assessment. |
| TDL | Implementation-level decision inside an approved architecture boundary. | Technical Decision Log entry. |
| Waiver | Temporary deviation from a required control or gate. | Waiver record with owner, risk, expiry, compensating control. |
| Research Note | Exploration without binding decision. | Non-authoritative note marked as draft/research. |

# 12. Sprint-0 Closeout and Handoff to Sprint 1

Sprint-0 closes with a formal readiness review. The review must demonstrate working controls and evidence, not only reported progress. The review should be conducted as a formal defense by the team: what was built, what was learned, what was improved, what risks remain, and whether Sprint 1 may begin.

| Closeout Item | Required Content |
| --- | --- |
| Foundation demo | Clone, build, run tests, run sample service, execute sample transaction, show CI evidence. |
| Evidence pack review | AVCI evidence, test reports, scan reports, architecture fitness, security review, decisions, waivers. |
| Open risk review | Unresolved issues, ownership, severity, target date, and whether they block Sprint 1. |
| Sprint 1 readiness | Approved backlog, module readiness criteria, owner assignments, and dependencies. |
| Lessons learned | What should be promoted to Obsidian/LLM Wiki after review and what should be improved in standards or templates. |

## 12.1 Ready-to-Code Decision Options

| Decision | Meaning | Allowed Next Step |
| --- | --- | --- |
| Approved | All critical gates pass; only non-blocking actions remain. | Start Sprint 1 controlled foundation and approved module work. |
| Approved with Conditions | Minor issues remain but have owners, expiry, and compensating controls. | Start limited Sprint 1 work that does not depend on open blockers. |
| Deferred | One or more critical gates failed or evidence is insufficient. | Continue Sprint-0 remediation; business coding remains blocked. |
| Rejected | Foundation approach violates architecture, security, or AVCI principles. | Escalate to Architecture Board and revise approach. |

# Appendix A. Sprint Board Template

| Column | Purpose | Entry Criteria | Exit Criteria |
| --- | --- | --- | --- |
| Backlog | Approved Sprint-0 stories not yet started. | Story has owner, acceptance criteria, classification, and dependency notes. | Story selected for active work. |
| Ready | Ready for development or configuration. | All dependencies are available and scope is clear. | Work has started. |
| In Progress | Actively being implemented. | Assigned owner working on task. | PR/MR or evidence artifact submitted. |
| Review | Awaiting code/config/security/architecture review. | PR/MR or artifact is complete and CI has run. | Reviewer approves or returns for rework. |
| Evidence Pending | Work is functionally complete but evidence is incomplete. | Implementation accepted but missing documentation or evidence. | Evidence pack updated. |
| Done | Meets acceptance criteria and evidence requirements. | All gates pass or approved waiver exists. | Included in closeout pack. |
| Blocked | Cannot progress without dependency or decision. | Blocker documented with owner. | Blocker resolved or escalated. |

# Appendix B. User Story Template

Sprint-0 User Story Template As a [role], I need [capability], so that [controlled outcome]. Acceptance criteria must include functional result, security/classification requirement, test evidence, architecture boundary requirement, and AVCI evidence.

| Field | Required Content |
| --- | --- |
| Story ID | S0-US-### |
| Title | Short action-oriented title. |
| User Story | As a role, I need a capability, so that a business/engineering outcome is achieved. |
| Classification | Public / Internal / Confidential / Restricted handling requirement. |
| Acceptance Criteria | Observable pass/fail criteria, including test and evidence expectations. |
| Architecture Impact | Service boundary, package, dependency, contract, or data ownership affected. |
| Security Impact | Identity, access, secrets, policy, model route, or audit impact. |
| Test Evidence | Required unit, component, contract, architecture, or security tests. |
| AVCI Evidence | Owner, source, verification, classification, improvement path. |

# Appendix C. Evidence Record Template

| Evidence Field | Required Value |
| --- | --- |
| evidence_id | Unique Sprint-0 evidence identifier. |
| artifact_name | Repository, pipeline, service, config, test, contract, migration, or document name. |
| owner | Named accountable person or role. |
| source_ref | Commit, PR/MR, ticket, ADR/TDL, or approved document reference. |
| classification | Public / Internal / Confidential / Restricted. |
| verification_method | Test, scan, review, demo, policy decision, manual inspection, or approval. |
| result | Pass, fail, blocked, waived, deferred. |
| principle_impact | SOLID, Clean Architecture, DDD, security, observability, reversibility, AVCI impact. |
| improvement_path | Backlog item, waiver expiry, review cadence, or monitoring signal. |

# Appendix D. AVCI Compliance Summary

| AVCI Property | Sprint-0 Application |
| --- | --- |
| Attributable | Each Sprint-0 story, artifact, repository setting, pipeline rule, service skeleton, contract, migration, and decision has a named owner and source reference. |
| Verifiable | Readiness is proven through build logs, test reports, architecture checks, scans, demo evidence, PR/MR reviews, and gate approvals. |
| Classifiable | Artifacts are labelled by sensitivity, domain, risk, evidence type, and handling rules; synthetic data is mandatory. |
| Improvable | Open issues, failures, lessons learned, and improvement candidates flow into the backlog, ADR/TDL, Obsidian/LLM Wiki, or standards update process. |

# Appendix E. Sprint-0 Sign-Off

| Role | Name | Decision | Signature / Date |
| --- | --- | --- | --- |
| Solutions Architect / IT Head |  |  |  |
| Software Development Lead |  |  |  |
| DevSecOps Lead |  |  |  |
| Security Administrator |  |  |  |
| System Administrator |  |  |  |
| Database Administrator |  |  |  |
| QA / SDET Lead |  |  |  |
| AI Engineering Lead |  |  |  |